## Year 2022
Weeks (Q1) | Project 1 | Weeks (Q2) | Project 2 | Weeks ( Q3 ) | Project 3 | Weeks ( Q4 ) | Project 4
2022-01-01 | Meeting: Project Plan | 2022-04-02 | Meeting: Project Plan | 2022-07-02 | Meeting: Project Plan | 2022-10-01 | Meeting: Project Plan
2022-01-08 | CI Setup Azure Cloud Shell | 2022-04-09 | CI Setup Azure Cloud Shell | 2022-07-09 | CI Setup Azure Cloud Shell | 2022-10-08 | CI Setup Azure Cloud Shell
2022-01-15 | CI Configure GitHub Actions | 2022-04-16 | CI Configure GitHub Actions | 2022-07-16 | CI Configure GitHub Actions | 2022-10-15 | CI Configure GitHub Actions
2022-01-22 | CD Azure Pipelines, Azure App Service | 2022-04-23 | CD Azure Pipelines, Azure App Service | 2022-07-23 | CD Azure Pipelines, Azure App Service | 2022-10-22 | CD Azure Pipelines, Azure App Service
2022-01-29 | Test: Deployment in Azure | 2022-04-30 | Test: Deployment in Azure | 2022-07-30 | Test: Deployment in Azure | 2022-10-29 | Test: Deployment in Azure
2022-02-05 | Stage: Deployment in Azure | 2022-05-07 | Stage: Deployment in Azure | 2022-08-06 | Stage: Deployment in Azure | 2022-11-05 | Stage: Deployment in Azure
2022-02-12 | Customer Testing / Feedback | 2022-05-14 | Customer Testing / Feedback | 2022-08-13 | Customer Testing / Feedback | 2022-11-19 | Customer Testing / Feedback
2022-02-19 | Change Request: Approval | 2022-05-21 | Change Request: Approval | 2022-08-20 | Change Request: Approval | 2022-11-28 | Change Request: Approval
2022-02-26 | Prod: Deployment in Azure | 2022-05-28 | Prod: Deployment in Azure | 2022-08-27 | Prod: Deployment in Azure | 2022-11-26 | Prod: Deployment in Azure
2022-03-05 | Customer / Feedback | 2022-06-04 | Customer / Feedback | 2022-09-03 | Customer / Feedback | 2022-12-03 | Customer / Feedback
2022-03-12 | Documentation / Training | 2022-06-11 | Documentation / Training | 2022-09-10 | Documentation / Training | 2022-12-10 | Documentation / Training
2022-03-19 |  | 2022-06-18 |  | 2022-09-17 |  | 2022-12-17 | Next Year Goals
2022-03-26 |  | 2022-06-25 |  | 2022-09-24 |  | 2022-12-24
| Goals |  | Goals |  | Goals |  | Goals
| Set up Infrastructure |  | Set up Infrastructure |  | Set up Infrastructure |  | Set up Infrastructure
| Continuous Integration |  | Continuous Integration |  | Continuous Integration |  | Continuous Integration
| Continuous Delivery |  | Continuous Delivery |  | Continuous Delivery |  | Continuous Delivery
| Testing |  | Testing |  | Testing |  | Testing
| Deployed Web Application Successfully |  | Deployed Web Application Successfully |  | Deployed Web Application Successfully |  | Deployed Web Application Successfully

## Q4
Weeks ( Q4 ) | Project 4
2022-10-01 | Meeting: Project Plan
2022-10-08 | CI Setup Azure Cloud Shell
2022-10-15 | CI Configure GitHub Actions
2022-10-22 | CD Azure Pipelines, Azure, App Service
2022-10-29 | Test: Deployment in Azure
2022-11-05 | Stage: Deployment in Azure
2022-11-19 | Customer Testing / Feedback
2022-11-28 | Change Request: Approval
2022-11-26 | Prod: Deployment in Azure
2022-12-03 | Customer / Feedback
2022-12-10 | Documentation / Training
2022-12-17 | Next Year Goals
2022-12-24
Goals
Set up Infrastructure
Continuous Integration
Continuous Delivery
Testing
Deployed Web Application Successfully